PROJECT MANAGEMENT

ANSWERS TO QUESTIONS

NAME : Manuel Kevin ZE FOUDA

- Problem to solve

Implementing a full information system security plan: auditing existing vulnerabilities, deploying MFA and EDR/Antivirus solutions, and strengthening the overall cybersecurity posture of the organization.

- Constraints

Strong sequential dependencies between tasks.

- Impact

| Stakeholder | Expectations |
| --- | --- |
| MOA, MOE | Budget approval, closure report, risk reduction |
| IT Administrators | Training, technical documentation |
| End Users | Cybersecurity awareness, adaptation to new tools |
| Project Manager | On-time and on-budget delivery |

- What events could cause the project to fail?

- Refusal or delay of budget approval

- Late delivery of MFA or EDR licenses

- Discovery of major vulnerabilities during testing requiring lengthy fixes

- Unavailability of administrators for training sessions

- Success criteria

- Closure meeting held

- Technical documentation delivered

- Security tests validated with no blocking anomaly

- MFA and EDR fully deployed and operational

- Duration : 36 Days

- End of the project : 24 November 2025

- Tasks belonging to the critical path

TASKS

Lancement du projet

Analyse de l’existant SI

Audit cybersécurité initial

Identification des vulnérabilités

Définition du plan de sécurisation

Validation budget direction

Achat licences MFA

Achat solution EDR/Antivirus

Déploiement MFA

Déploiement solution EDR

Tests de sécurité et validation

Corrections anomalies

Documentation technique

Formation administrateurs IT

- Regroup tasks

- Which activities can be carried out simultaneously to optimize the schedule?

The 4 non-critical tasks can run in parallel with critical tasks :

- Firewall update

- Secure backup configuration

- User cybersecurity awareness

- Phishing test campaign

These tasks carry float and do not extend the overall duration if properly scheduled.

- If the CEO requires a 20% schedule reduction, what do you propose?

New end date:  36 days – 20% equals to 29 working days. So the new end date will be on November 13, 2025.

My proposals:

- Anticipate license orders before formal budget sign-off (conditional purchase order)

- Compress Initial cybersecurity audit from 5d to 3d by assigning a two-person audit team

- Compress MFA/EDR deployments from 5d to 3d with a reinforced deployment team;

- Merge documentation and training simultaneously over 2 days instead of sequentially

- GANTT Diagram:

- Project statistics: